## Cover Page
STATE BUSINESS-ENABLING REFORM ACTION PLANS (BERAP) PROGRESS REPORT
State: | KWARA
Reporting period: |  | FY 2025
SABER Focal Person: |  |  | DR HAUWA NUHU, COMMISSIONER FOR FINANCE
Was this plan prepared in consultation with the Private Sector |  |  |  |  | Yes
List of contributing entities: |  |  |  | Min of Finance, Ministry of Budget, Kwara State Internal Reveni=ue Servcices, |  |  | Revenue Services | NAEMA, RIFAN, Private Sectors, NGOs etc
URL Link to the published BERAP
Is this plan approved by the State Executive Council (SEC) |  |  |  |  | Yes | Choose as appropriate
If this was approved by SEC, please state date:
Please further to proof of private sector consultation, please include for the purpose of the Verification Protocol: (a) summary of private sector consultation, and (b) list of private sector participants invited to the consultation – including name, organization, designation of representative, phone number and email address and other information as may be deemed relevant

## BERAP
1 |  | KWARA STATE 2025 BERAP PROGRESS REPORT
| BUSINESS ENABLING REFORM AREA | REFORM OBJECTIVES | ACTION STEPS | DESCRIPTION AND KEY TARGET AREAS | RESPONSIBLE MDAs | CONTRIBUTING MDAs | Beneficiaries | BUDGET | PLANNED START DATE | PLANNED END DATE | STATUS | DESCRIPTION STATUS | NEXT STEP
1 | LAND ADMINISTRATION | 1. To achievement efficiency in Property registration 2. To engender transparency and Integrity in Land administartion in Kwara State 3. Automate the processes of obtaining lands for investment purposes , | 1.All Land records are digitalised 2.Harmonisation of payment system 3. Consolidation of CofO related apllications | 1.50% Reduction in time taken to process CofO applications 2. 100% increase in Property registration with full automation | Kwara State Geographical Information Service. | Kwara State Internal Revenue Service | Individuals, Business owners( Hotels, Schools,) , shop owners, Farmers, Filling Stations. Banks, Hospitals. | N250M | Jan1,2025 | Dec 31,2025 | Completed | All land administration processes have been synchronized and digitized. The harmonized payment platform and digital processing of land records have significantly improved transparency and reduced the processing time for Certificates of Occupancy (C of O). | Quarterly monitoring system performance, maintain the digital platform, and provide periodic user support and system upgrades.
2 | INVESTMENT IN LAND BASED AGRICULTURE | To create awareness about the implementation of The Framework For Responsible And Inclusive LandIntensive Agriculture (FRILIA) in the State | Presentation of the Framework For Responsible And Inclusive LandIntensive Agriculture (FRILIA) stakeholders Engagement and Communication strategy, including The Framework For Responsible And Inclusive LandIntensive Agriculture(FRILLIA) Greviance Remedial Mechanism | b | Ministry of Agriculture | Kwara State Geographical Information Service, Kwar State Investment Prommotion Agency, Ministry of Finance, Ministry of Business Innovation & Technology | Farmers. | N200M | Jan1,2025 | Dec 31,2025 | Completed | The FRILIA Stakeholder Engagement and Communication Strategy, including the FRILIA Grievance Redress Mechanism (GRM), has been developed and presented to key stakeholders. Awareness creation activities are ongoing to promote responsible and inclusive land-based agricultural investments across the State. | Bi- annual statewide stakeholder sensitization, operationalize the Grievance Redress Mechanism, monitor compliance with FRILIA principles, and integrate the framework into all eligible land-intensive agricultural investments
3 | JUSTICE DELIVERY | 1. To create easy access to justice 2. To deepen the confidence of prospective justice seekers/Litigants | Designation of more Margistration as Small Claims Courts 2. Equipping of Small Claims court Registry 3.Training of Magistrates and Small Claims Courts Officials | 1. Training of 20 Magistrates and 20 Court Officials 2. Provision of four Computers for Small Claims Courts Registry. 3. performance tracking to ensure that at least 50% of cases are completed within the 60-day timeline | Kwara State Judiciary | Ministry of Justice, Kwara State Internal Revenue Service and Ministry of Finance. | Small sclae Businesses, Hotels, schools, Artisans, Entreprenuers. | N150M | Jan1,2025 | Dec 31,2025 | Completed | Additional Magistrates have been designated for Small Claims Courts. Procurement of ICT equipment for the registry was done, while training programmes for Magistrates and court officials are being implemented to strengthen efficient justice delivery. | Complete procurement and installation of ICT equipment, conclude capacity-building programmes, and commence performance monitoring to ensure at least 70% of cases are concluded within the 60-day timeline.
4 | INFORMAL SECTOR TAX REGIME | 1. To extend the tax net to cover more of the informal sector 2.To achieve full electronic Tax administration 3. To improve the State IGR | 1.Full Automation of Kwara State Internal Revenue Service Internal Operations 2. Training and capacity building of IIRS staff for operational efficiency | 1. 50% IGR increase. 2. Training of 100 members of staff of IIRS . 3. Training of 150 business men on the IIRS electronic payment system | Kwara State Internal Revenue Service | Ministry of finance , Ministry of Business Innovation. KWACCIMA | Artisans, Market women, Bakers, farmers, Schools | N100M | Jan1,2025 | Dec 31,2025 | Completed | Automation of the Internal Revenue Service's internal operations is progressing, while staff capacity-building programmes and taxpayer sensitization on electronic tax payment was concluded. These initiatives are enhancing tax administration efficiency and voluntary compliance | Complete system automation, expand taxpayer education across the informal sector, continue staff training, and monitor revenue performance and e-payment adoption. The sxercises shall be done bi annual , except the training of staff will be done quartely.
5 | INVESTMENT IN FIBRE OPTIC INFRASTRUCTURE | To encourage private Investments in Fibre Optic Infrastructure | 1 State wide sensitization campaign on the Executive Order on ROW 2. Stakeholders Engagement on the Processes and Procedures of ROW Application in the State | 1. Two Sessions of Stakeholders Engagement, 2. Two publications on Print and Electronic media | Kwara State Geographical Information Service, Ministry of Works | Ministry of Bussiness Innovation | Telcommunication companies. | N60M | Jan1,2025 | Dec 31,2025 | Completed | Stakeholder engagement and sensitization on the Right-of-Way (RoW) Executive Order have commenced. Awareness campaigns are promoting the simplified application procedures and encouraging private investment in broadband infrastructure. | Conduct additional stakeholder engagement sessions quarterly to sustain media awareness campaigns, and monitor private sector investments in fibre optic infrastructure. | s
6 | PUBLIC, PRIVATE PARTNERSHIP | 1.Development of PPP in the State 2. To encourage Partnership investments in the state Economy, | 1. Stakeholders Engagements on Investment Potentials/ Incentives in the State. | 1. Organize four sessions of stakeholders Engagement | Kwara State Investment Promotion Agency | Ministry of finance , Ministry ofBusiness Innovation, KWACCIMA, | Contractors, Hotels, schools, Hospitals. | N150M | Jan1,2025 | Dec 31,2025 | completed | Stakeholder engagements on investment opportunities and Public-Private Partnership initiatives have commenced. Investment promotion activities are attracting private sector participation in strategic sectors of the State economy | Organize additional investment forums, strengthen investor engagement, finalize partnership discussions, and facilitate execution of viable PPP projects
7 | TRANSPERANCY OF OFFICIAL FEES & PROCEDURES | To boost stakeholders' confidence in the services of Government | Conduct sensitization programs on the benefits of Service Level Agreements, GRM and Mandatory advance communication Rules of upcoming changes | 1. Organize Six sessions of stakeholders Engagement. 2 publication of the Service Level Agreements on the state official website and implementation of the Grievance Remedial Mechanisms. | Ministry of Business Innovation & Technology | Kwara State Geographical Information Service, Ministry of Works, Kwara State Internal Revenue Services, Minstry of Education, Ministry of Agriculture &Natural Resoiurces. | Manufacturers, schools, Farmers, Maanufacturers, Hotels. | N120M | Jan1,2025 | Dec 31,2025 | Delayed | The reform activity has been delayed for approximately nine (9) months beyond the December 2025 implementation timeline. The delay resulted from the need to harmonize and validate Service Level Agreements (SLAs) across the implementing MDAs to ensure consistency with their respective operational procedures. In addition, prolonged stakeholder consultations, administrative approval processes, and competing government priorities affected the timely publication of the SLAs and the full implementation of the Grievance Redress Mechanism (GRM). Consequently, the reform could not be fully completed within the 2025 implementation period, although substantial progress has been made | Complete the harmonization, approval, and publication of all outstanding Service Level Agreements on the State's official website by September 2026. 2. Conduct stakeholder sensitization and awareness programmes on the Service Level Agreements, Mandatory Advance Communication Rules, and the Grievance Redress Mechanism by September 2026. 3. Strengthen and institutionalize the implementation of the Grievance Redress Mechanism across all implementing MDAs. 4. Conduct compliance monitoring and support visits to implementing MDAs in July and November 2026 to ensure full implementation and sustainability of the reform.
8 | EXPORT PROMOTION | Promotion of Exportable Goods | Implememtation of the State Export Prommtion strategy 2. To encourage the State Committee on Export Prommotion to achieve its mandate | Quarterly sensitization on access to credit . 2. Three sessions of the Export potentials of the State | Ministry of Business Innovation & Technology | Kwara State Investment Promotion Agency, Kwara State Internal Revenue ServicesS, Ministry of Finance. | Farmers, Bakers, School, Manufactures, Banks. | N150M | Jan1,2025 | Dec 31,2025 | Completed | Implementation of the State Export Promotion Strategy has been concluded: Stakeholder sensitization on export opportunities and access to finance is ongoing, while the State Export Promotion Committee continues to coordinate export development initiatives | Bi annual sensitization programmes, strengthen the capacity of exporters, facilitate access to export financing, and monitor implementation of the State Export Promotion Strategy.

## Progress Report (hidden)
BUSINESS-ENABLING REFORM ACTION PLAN (BERAP) PROGRESS REPORT
Original action plan as published | [9 empty] | Progress Update
S/N | Business Enabling Reform Areas | Reform Objectives | Action Steps | Description and Key Targets | Responsible MDA | Contributing MDAs | Budget | Planned Start Date | Planned End Date | Status | Description of Status | Next Steps
| The focus area for the reforms eg transparency of official fees and procedures | What the State intends to achieve by implementing the Business Enabling Reform | Very detailed, step by step process on how the objective will be achieved | User, beneficiaries, recipient of the reform Explain actions and/or sub-actions and include targets | One MDA responsible for the action/activity | Supporting MDAs | Estimated budget for the action/activity | When you commit to start the implementation of the actions | When you commit to complete the actions and achieve tour targets | Indicate whether the action/activity is completed, ongoing - on time, ongoing - delayed or dropped | Describe the status of each action, explaining reasons for any delays or actions being dropped. Explain any changes that occurred during implementation affecting start and end dates | Describe next steps for the outstanding actions. For example, is the action getting carried over to the following year's action plan?
1 | Illustrative example: Transparency of official fees and procedures | Illustrative example: This reform area will increase transparency of official fees and procedures focusing on key business environment enabling MDAs | Illustrative example A. Finalise process mapping of one business regulatory area number 1 | A description of the action and target, e.g. business regulatory process mapping signed off by all included MDAs and approved by the relevant authority | List the one MDA that would be responsible for this action/activity | List the several MDAs that would actively contribute to the activity | Amount (in Naira) | Day, Month, Year | Day, Month, Year
Illustrative example A.1. Map existing process for carrying out impact evaluation
B.
B.1
B.2
C.
C.1
C.2